## Slide 1
Implementing Meditech Expanse
– The Continuation

## Slide 2
Ireland’s largest private hospital group
5 Hospitals
1 Care Village
500+ Consultants
400,000+ Patients Annually
4000+ Employees

## Slide 3
LIMERICK
TRALEE
CORK
GALWAY
DUBLIN
Hospital Network

## Slide 4
New Limerick Hospital – Now Open
Notes: Some of the key services of the new hospital include
99 inpatient rooms
A cath lab
Medcial Assessment unit
And dedicated ophthalmology unit

## Slide 5
Geoffrey Cordner
Revenue Cycle
Working
Groups
Systems Integration
Data Migration
Infrastructure
Reporting and Business Intelligence
Security / Compliance & Data Protection
Clinical Steering Committee
Clinical Standards, Interprofessional Assessment, Documentation, Workflows; Order Sets and P. Doc
BonsConnect Programme Board
BonsConnect Steering Committee
Cliona Byrne
Programme Director
Alison MacDonald
Nordic Consulting Lead
Board Finance Committee
Margaret McHugh
Programme Executive Sponsor
Clinical
Dr Hannah Ryan
Technical
Darragh McNally
Revenue Cycle
David Scannell & Derek Kirwan
PMO Team
Stream Leads (Revenue, Technical, Clinical & Pathology)
Project Managers (Revenue & Clinical)
Clinical Transformation Lead
Communications Manager
Training Lead
Stream
Leads
David Hingston
Stream
Project Managers
Project
Management Office
Executive
Governance
The Programme Board provides strategic oversight of the programme and approves any changes including timelines, budget, or scope. Membership includes the Group CEO, CFO, CRO, Chief Nursing, Quality & Patient Safety Officer, and BSHL’s Chief Clinical Information Officer.
The Steering Committee provides operational oversight of the delivery of the programme, overseeing resourcing, contracting, project status reporting, and other matters of programme execution. Membership includes the CIO, CCO, Hospital CEOs, Finance, Stream Leads, Compliance, the Programme Directors together with Vice President Information & Technology, Bon Secours Mercy Health.
GOVERNANCE
Radiology
Inpatient Medicine
Medical Records (HIM)
Nursing & HSCP
Oncology
Pathology
Patient Access
Pharmacy
Theatre
Outpatient and Diagnostics
BON SECOURS MERCY HEALTH
Director of Internal Audit
BonsConnect Programme Board
Programme specialists and analysts
Board Finance Committee
Weekly meetings between Meditech and BonsConnect Project Management Teams
Project Management Team
BonsConnect Steering Committee
Janine Higgins

## Slide 6
Taking Stock
Notes: When I spoke last year we were planning for a Go live in June of this year and this did not come to pass.
Early this year we found we were not were we hoped nor expected to be and it became clear we need to pause and take stock

## Slide 7
Programme Team Taking Stock
Scope Review
Each Working Group undertook a Deliverables Review individually
Deliverables Review as a Team
Critical Path Review
Timeline Review

## Slide 8
Programme Team Taking Stock
Strengths
Teams Knowledge of the System
Positive Engagement
Level of build completed for some groups
Commitment to the Programme
Challenges
Volume of Build Remaining
Groups working in silos
Decisions and Standardisation taking longer than anticipated
User Acceptance Testing
Running events in parallel; Future State / UAT / Prep for Training

## Slide 9
Organisational Change Management

## Slide 10
Stakeholders required understanding of the deliverables
Involvement of Management Teams from Sites in deliverables
Working Group Leads report into Stakeholders
Increase Membership of the Steering Committee
Site Readiness Focus Increased
Testing Feasibility of the Proposed Timelines
Actions to Improve Organisational Readiness

## Slide 11
Build Freeze Date Agreed
Critical Path Consolidation
Reviewed Timeline Accepted
Site Order Reviewed and Accepted
Additional Resources Secured – Internal and External
Programme Team Contract Lengths Extended
User Acceptance Testing Event for 5 Hospitals Agreed
Regular in-depth reviews with all Stakeholders
Main Factors Resulting for Taking Stock

## Slide 12
TIMELINE
Work Plan
Charter
Team
Governance Model
Kick-off
Contract Vendor
Recruitment & Resources
Programme
Alignment
2023
2023
2024
2025
2025
Year
Phase
Gates
Phase
Objective
Deliverable
Highlights
Phase
Gate
Detail
2
1
Standardise Clinical and Business Content
Establish working groups
Guiding Principles
Standards and templates
Begin Workflow and Process Re-design
Launch Change Management Programme
3
Train working groups
System configuration
Conversion & Interface
Testing
Change Management
Configure & Test System
6
Prototyping 3
5
E-learning
Classroom Training
Verify Production Readiness
System In Production
Go-Live
Above base staffing
Personalisation
Training
7
Go Live 1 & 2
7
Service to Support Handover
Go-Live Support
Issue Resolution
Lessons Learned
Transition to Operational Model
Post Go-Live Support
Project Phase
Standardisation
Build & Test
Train & Go Live
Preplanning
Stabilise & Optimise
May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept
Programme Approval
1
Kick off
2
2024
4
Guiding Principles
3
4
Project Team Training Commences
2024
Progress to date
5
Readiness Assessment
(180 days)
6

## Slide 13
TIMELINE
2025
2025
Year
Gates
Phase
Objective
Deliverable
Highlights
Critical Path
Standardise Clinical and Business Content
Workflow Standardisation
What Remains on Paper
Policies and Procedures
Organisational Readiness
3
System Build
Conversion Testing
Interface Testing
Unit Testing
User Acceptance Testing
Targert Testing
Revenue I Testing
Copy to Live
Configure & Test System
Build Freeze
E-learning
Classroom Training
Video Content
Cribsheets
Training Cirrculum
Super User Training
End User Training
Training
Go Live 1
Go-Live
Project Phase
Standardisation
Build & Test
Training
Go Live
Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec
4
3
4
Where we are
1
2024
Jan | Feb | Mar | April
Site Readiness
Cut Over Planning
Activation Planning
Go-Live Planning
Migration
Cut Over
Go Live
5
2
3
1
2
3
User Acceptance Testing
Test to Live Copy
5
Gate 5 - Pre Go Live – Data Protection and Security tests.
Gate 4 - Governance for post go live arrangements
Gate 3 - Light Up of System Interfaces & Full Data Conversion Migration
Gates

## Slide 14
User Acceptance Testing

## Slide 15
UAT for all 5 hospitals – 2 weeks onsite in Tralee
Week #1
UAT Phase: Week 1 – Core UAT Surgical/Medicine/Critical Care Scenarios
Date Range: 8th - 12th September
Sites Tested: Tralee & Limerick
Workflows Tested: Pre-assessment, Medical Assessment Unit, Medical Inpatient, Surgical Inpatient, Critical Care, Medical Day Unit, Surgical Day Unit
In Scope: Registration, Admissions, Scheduling, Nursing, NCHD, Lab, Pharmacy, Physiotherapy, Orders, Revenue Cycle, Medical Records & Transfusion Administration Record (TAR)
User Acceptance Testing

## Slide 16
UAT for all 5 hospitals – 2 weeks onsite in Tralee
Week #2
UAT Phase: Week 2 – Endoscopy, Cath lab and Outpatient Clinics
Date Range: 15th - 19th September
Sites Tested: Tralee & Limerick
Workflows Tested: Endoscopy, Radiology, Minor Ops, CNS Led Clinics, Cath lab, Physiotherapy, Deictics, Cardiology, Occupational Therapy, Respiratory Clinics
In Scope: Registration, Admissions, Scheduling, Nursing, NCHD, Lab, Physiotherapy, Radiology, Occupational Therapy, Cardiology, Respiratory, Revenue Cycle, Medical Records, CVIS & EndoRaad
User Acceptance Testing

## Slide 17
Questions ?